## SANKYU Saudi Arabia
SHIPMENT STATUS REPORT 2018-04-23 SANKYU Saudi Arabia SUMITOMO
No | SR. no. | Our Job No | Customer Name | Order No. | Shipment Received Date | B/L Number | Number Of Containers |  | Terminal | Shipping Line | Vessel Name | ETA |  | CC Days | Manifest documents Received Date | Bayan NO. | Rotation NO. | Initial Bayan Date | Pre-Bayan | Manifest to Initial Bayan Printed | Initial Bayan to Pre Bayan Printed | Shuttling |  | Final Bayan Date | Shuttle to final bayan | Random Inspection | Custom Exam Of Containers no. | New Seal no. | Load Permit Printed On | Total Expenses |  |  |  | Status | Remarks | Reason for the delay (Shutout) (If any)
[7 empty] | 20ft | 40ft |  |  |  | On or About | Revised ETA Date | [8 empty] | Start Date | End Date | [6 empty] | Custom Duty | Inspection | Container Seal | Total
1 | S0050 | J0050 | SANKYU Saudi Arabia | 4900004572 | 2018-01-04 | MSCUJ5546146 |  | 2 | - |  | SOLA | 2018-01-11 | 2018-01-11 | 7 | 2018-01-04 | 242 | 956 | 2018-01-04 | 2018-01-06 | 2 | 2 | 2018-01-04 | 2018-01-07 | 2018-01-07 | 3 |  |  |  |  | / | / | / | / | Completed
2 | S0051 | J0051 | SANKYU Saudi Arabia | 4900004573 | 2018-01-04 | MSCUJ5546195 |  | 11 | - |  | SOLA | 2018-01-11 | 2018-01-11 | 7 | 2018-01-04 | 241 | 956 | 2018-01-04 | 2018-01-06 | 2 | 2 | 2018-01-04 | 2018-01-07 | 2018-01-07 | 3 |  |  |  |  | / | / | / | / | Completed
3 | S0093 | J0093 | SANKYU Saudi Arabia | 4900004570 | 2018-01-08 | HLCUJE2171225004 |  | 9 | - |  | MSC HEIDI IP808R | 2018-01-06 | 2018-03-06 | -2 | 2018-03-03 | 2601 | 174/27 | 2018-03-06 | 2018-03-06 | 3 | 0 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 0 |  |  |  |  | / | / | / | / | Completed
4 | S0157 | J0157 | SANKYU Saudi Arabia | 4600012983 | 2018-01-11 | MSCUJ5549843 |  | 6 | - |  | MSC FABIOLA | 2018-01-25 | 2018-01-25 | 14 | 2018-01-21 | 710 | 28/47 | 2018-01-21 | 2018-01-22 | 1 | 1 | 2018-01-22 | 2018-01-23 | 2018-01-23 | 1 |  |  |  |  | / | / | / | / | Completed
5 | S0164 | J0164 | SANKYU Saudi Arabia | 4900004547 | 2017-12-28 | HLCUJE2171228437 | 7 |  | - |  | MSC BHUSAN | 2017-12-26 | 2018-01-17 | -2 | 2018-01-10 | 413 | 18/27 | 2018-01-13 | 2018-01-14 | 4 | 1 | 2018-01-14 | 2018-01-15 | 2018-01-15 | 1 |  |  |  |  | / | / | / | / | Completed
6 | S0173 | J0173 | SANKYU Saudi Arabia | 4900004564 | 2018-01-14 | HLCUJE2180111980 |  | 2 | - |  | MSC TOMOKO | 2018-01-30 | 2018-01-30 | 16 | 2018-01-25 | 888 | 52/24 | 2018-01-25 | 2018-01-25 | 0 | 0 | 2018-01-26 | 2018-01-27 | 2018-01-27 | 1 |  |  |  |  | / | / | / | / | Completed
7 | S0174 | J0174 | SANKYU Saudi Arabia | 4900004568 | 2018-01-14 | MSCUJ5549785 | 9 |  | - |  | MSC Fabiola | 2018-01-25 | 2018-01-25 | 11 | 2018-01-18 | 653 | 28/42 | 2018-01-18 | 2018-01-20 | 2 | 2 | 2018-01-20 | 2018-01-21 | 2018-01-21 | 1 |  |  |  |  | / | / | / | / | Completed
8 | S0175 | J0175 | SANKYU Saudi Arabia | 4900004567 | 2018-01-14 | HLCUJE2180119609 | 9 |  | - |  | MSC HEIDI | 2018-03-06 | 2018-03-06 | 51 | 2018-02-28 | 2370 | 96/25 | 2018-02-28 | 2018-02-28 | 0 | 0 | 2018-03-01 | 2018-03-03 | 2018-03-03 | 2 |  |  |  |  | / | / | / | / | Completed
9 | S0274 | J0274 | SANKYU Saudi Arabia | 4500026930 | 2018-01-22 | MSCUJ5551575 | 1 |  | - |  | MSC IRENE | 2018-02-03 | 2018-02-03 | 12 | 2018-01-23 | 832 | 61/19 | 2018-01-24 | 2018-01-25 | 2 | 1 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 0 |  |  |  |  | / | / | / | / | Completed
10 | S0299 | J0299 | SANKYU Saudi Arabia | 4500026931 | 2018-01-24 | MSCUJ5553001 | 6 |  | - |  | MSC ROSA | 2018-01-28 | 2018-01-28 | 4 | 2018-01-25 | 894 | 66/10 | 2018-01-25 | 2018-01-25 | 0 | 0 | 2018-01-26 | 2018-01-27 | 2018-01-27 | 1 |  |  |  |  | / | / | / | / | Completed
11 | S0373 | J0373 | SANKYU Saudi Arabia | 4900004621 | 2018-01-28 | MSCUJ5555972 | 1 |  | - |  | MSC FRANCESCA | 2018-02-08 | 2018-02-08 | 11 | 2018-02-03 | 1269 | 79/63 | 2018-02-03 | 2018-02-03 | 0 | 0 | 2018-02-03 | 2018-02-04 | 2018-02-04 | 1 |  |  |  |  | / | / | / | / | Completed
12 | S0374 | J0374 | SANKYU Saudi Arabia | 4500027028 | 2018-01-28 | MSCUJ5553829 | 1 |  | - |  | MSC DANIELA | 2018-02-04 | 2018-02-04 | 7 | 2018-01-31 | 1147 | 68/10 | 2018-01-31 | 2018-01-31 | 0 | 0 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 0 |  |  |  |  | / | / | / | / | Completed
13 | S0375 | J0375 | SANKYU Saudi Arabia | 4500026985 | 2018-01-28 | MSCUJ5553811 | 2 |  | - |  | MSC IRENE | 2018-02-02 | 2018-02-02 | 5 | 2018-01-28 | 1023 | 61/40 | 2018-01-29 | 2018-01-29 | 1 | 0 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 0 |  |  |  |  | / | / | / | / | Completed
14 | S0569 | J0569 | SANKYU Saudi Arabia | 4500027128 | 2018-02-08 | MSCUJ5558737 | 5 |  | - |  | MSC DEILA | 2018-02-18 | 2018-02-18 | 10 | 2018-02-13 | 1583 | 113/7 | 2018-02-13 | 2018-02-13 | 0 | 0 | 2018-02-14 | 2018-02-14 | 2018-02-14 | 0 |  |  |  |  | / | / | / | / | Completed
15 | S0570 | J0570 | SANKYU Saudi Arabia | 4500027099 | 2018-02-08 | MSCUJ5558745 | 10 |  | - |  | MSC DEILA | 2018-02-18 | 2018-02-18 | 10 | 2018-02-13 | 1618 | 113/5 | 2018-02-13 | 2018-02-13 | 0 | 0 | 2018-02-14 | 2018-02-15 | 2018-02-15 | 1 |  |  |  |  | / | / | / | / | Completed
16 | S0630 | J0630 | SANKYU Saudi Arabia | 4500027187 | 2018-02-11 | MSCUJ5559834 | 8 |  | - |  | MSC DEILA | 2018-02-18 | 2018-02-18 | 7 | 2018-02-13 | 1584 | 113/11 | 2018-02-13 | 2018-02-13 | 0 | 0 | 2018-02-14 | 2018-02-14 | 2018-02-14 | 0 |  |  |  |  | / | / | / | / | Completed
17 | S0631 | J0631 | SANKYU Saudi Arabia | 4500027188 | 2018-02-11 | MSCUJ5559842 | 4 |  | - |  | MSC DEILA | 2018-02-18 | 2018-02-18 | 7 | 2018-02-13 | 1585 | 113/10 | 2018-02-13 | 2018-02-13 | 0 | 0 | 2018-02-14 | 2018-02-14 | 2018-02-14 | 0 |  |  |  |  | / | / | / | / | Completed
18 | S0632 | J0632 | SANKYU Saudi Arabia | 4500027133 | 2018-02-11 | MSCUJ5558885 |  | 4 | - |  | MSC GAIA | 2018-02-17 | 2018-02-15 | 6 | 2018-02-13 | 1620 | 92/26 | 2018-02-13 | 2018-02-13 | 0 | 0 | 2018-02-14 | 2018-02-15 | 2018-02-15 | 1 |  |  |  |  | / | / | / | / | Completed
19 | S0633 | J0633 | SANKYU Saudi Arabia | 4500027166 | 2018-02-11 | MSCUJ5558901 | 4 |  | - |  | MSC DEILA | 2018-02-18 | 2018-02-18 | 7 | 2018-02-12 | 1572 | 113/6 | 2018-02-13 | 2018-02-13 | 1 | 0 | 2018-02-14 | 2018-02-14 | 2018-02-14 | 0 |  |  |  |  | / | / | / | / | Completed
20 | S0784 | J0784 | SANKYU Saudi Arabia | 4500027205 | 2018-02-18 | MSCUJ5561889 | 6 |  | - |  | MAERSK HORSBURGH | 2018-02-21 | 2018-02-21 | 3 | 2018-02-18 | 1866 | 140/24 | 2018-02-19 | 2018-02-19 | 1 | 0 | 2018-02-20 | 2018-02-20 | 2018-02-20 | 0 |  |  |  |  | / | / | / | / | Completed
21 | S0788 | J0788 | SANKYU Saudi Arabia | 4500027202 | 2018-02-18 | MSCUJ5562267 | 16 |  | - |  | MAERSK HORSBURGH | 2018-02-22 | 2018-02-22 | 4 | 2018-02-19 | 1956 | 140/25 | 2018-02-20 | 2018-02-20 | 1 | 0 | 2018-02-21 | 2018-02-21 | 2018-02-21 | 0 |  |  |  |  | / | / | / | / | Completed
22 | S0789 | J0789 | SANKYU Saudi Arabia | 4500027203 | 2018-02-18 | MSCUJ5562259 | 12 |  | - |  | MSC RAVENNA | 2018-02-26 | 2018-02-26 | 8 | 2018-02-21 | 2103 | 160/3 | 2018-02-22 | 2018-02-22 | 1 | 0 | 2018-02-23 | 2018-02-25 | 2018-02-25 | 2 |  |  |  |  | / | / | / | / | Completed
23 | S0855 | J0855 | SANKYU Saudi Arabia | 4500027239 | 2018-02-21 | MSCUJ5564552 | 5 |  | - |  | MSC VALERIA | 2018-03-01 | 2018-03-01 | 8 | 2018-02-26 | 2533 | 179/18 | 2018-03-05 | 2018-03-05 | 7 | 0 | 2018-03-06 | 2018-03-07 | 2018-03-07 | 1 |  |  |  |  | / | / | / | / | Completed
24 | S0936 | J0936 | SANKYU Saudi Arabia | 4500027270 | 2018-02-27 | MSCUJ5566474 |  | 11 | - |  | MSC AURORA | 2018-03-10 | 2018-03-10 | 11 | 2018-02-28 | 2361 | 179/2 | 2018-02-28 | 2018-02-28 | 0 | 0 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 0 |  |  |  |  | / | / | / | / | Completed
25 | S1011 | J1011 | SANKYU Saudi Arabia | 4500027321 | 2018-03-01 | MSCUJ5567753 | 9 |  | - |  | MSC BARI | 2018-03-04 | 2018-03-04 | 3 | 2018-03-03 | 2496 | 167/9 | 2018-03-04 | 2018-03-04 | 1 | 0 | 2018-03-05 | 2018-03-06 | 2018-03-06 | 1 |  |  |  |  | / | / | / | / | Completed
26 | S1149 | J1149 | SANKYU Saudi Arabia | 4500027337 | 2018-03-11 | MSCUJ5570062 | 6 |  | - |  | EMMA MAERSK | 2018-03-19 | 2018-03-19 | 8 | 2018-03-11 | 2829 | 220/10 | 2018-03-14 | 2018-03-14 | 3 | 0 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 0 |  |  |  |  | / | / | / | / | Completed
27 | S1421 | J1421 | SANKYU Saudi Arabia | 4500027553 | 2018-03-26 | MSCUJ5576820 | 4 |  | - |  | MAERSK HIDALGO | 2018-03-31 | 2018-03-31 | 5 | 2018-03-28 | 3357 | 260/18 | 2018-03-28 | 2018-03-28 | 0 | 0 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 0 |  |  |  |  | / | / | / | / | Completed
28 | S1422 | J1422 | SANKYU Saudi Arabia | 4500027554 | 2018-03-26 | MSCUJ5576796 |  | 4 | - |  | MAERSK HIDALGO | 2018-03-31 | 2018-03-31 | 5 | 2018-03-28 | 3358 | 260/18 | 2018-03-28 | 2018-03-28 | 0 | 0 | 2018-03-29 | 2018-03-31 | 2018-03-31 | 2 |  |  |  |  | / | / | / | / | Completed
29 | S1423 | J1423 | SANKYU Saudi Arabia | 4500027538 | 2018-03-26 | MSCUJ5577786 |  | 4 | - |  | MAERSK HIDALGO | 2018-03-28 | 2018-03-28 | 2 | 2018-03-28 | 3551 | 260/27 | 2018-04-01 | 2018-04-01 | 4 | 0 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 0 |  |  |  |  | / | / | / | / | Completed
30 | S1424 | J1424 | SANKYU Saudi Arabia | 4600013789 | 2018-03-26 | MSCUJ5576788 | 7 |  | - |  | MSC FRANCESCA | 2018-03-29 | 2018-03-29 | 3 | 2018-03-28 | 3356 | 253/23 | 2018-03-28 | 2018-03-28 | 0 | 0 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 0 |  |  |  |  | / | / | / | / | Completed
31 | S1425 | J1425 | SANKYU Saudi Arabia | 4900004721 | 2018-03-26 | MSCUJ5576770 | 3 |  | - |  | MSC FRANCESCA | 2018-03-29 | 2018-03-29 | 3 | 2018-03-28 | 3354 | 253/20 | 2018-03-28 | 2018-03-28 | 0 | 0 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 0 |  |  |  |  | / | / | / | / | Completed
32 | S1458 | J1458 | SANKYU Saudi Arabia | 4500027619 | 2018-03-26 | MSCUJ5576416 |  | 4 | - |  | MSC CAMILLE | 2018-04-07 | 2018-04-07 | 12 | 2018-03-26 | 3495 | 267/3 | 2018-03-29 | 2018-03-29 | 3 | 0 | 2018-03-30 | 2018-04-01 | 2018-04-01 | 2 |  |  |  |  | / | / | / | / | Completed
33 | S1571 | J1571 | SANKYU Saudi Arabia | 4500027672 | 2018-04-01 | MSCUJ5579501 |  | 4 | - |  | MSC IRENE | 2018-04-02 | 2018-04-02 | 1 | 2018-04-02 | 3617 | 277/2 | 2018-04-02 | 2018-04-02 | 0 | 0 | 2018-04-03 | 2018-04-04 | 2018-04-04 | 1 |  |  |  |  | / | / | / | / | Completed
34 | S1655 | J1655 | SANKYU Saudi Arabia | 4500027791 | 2018-04-03 | MSCUJ5580798 |  | 7 | - |  | MSC IRENE | 2018-04-13 | 2018-04-13 | 10 | 2018-04-05 | 3863 | 277/21 | 2018-04-07 | 2018-04-07 | 2 | 0 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
35 | S1692 | J1692 | SANKYU Saudi Arabia | 4500027799 | 2018-04-04 | MSCUJ5580921 |  | 12 | - |  | MSC IRENE | 2018-04-13 | 2018-04-13 | 9 | 2018-04-05 | 3862 | 277/20 | 2018-04-07 | 2018-04-07 | 2 | 0 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
36 | S1797 | J1797 | SANKYU Saudi Arabia | 4500027807 | 2018-04-11 | MSCUJ5582968 |  | 14 | - |  | MSC RAPALLO | 2018-04-13 | 2018-04-13 | 2 | 2018-04-12 | 4076 | 290/23 | 2018-04-14 | 2018-04-14 | 2 | 0 | 2018-04-15 | 2018-04-16 | 2018-04-16 | 1 |  | BMOU4834132/BMOU6624496/DRYU9084854/MEDU4172525/MEDU8355946/TCKU4009917/TGCU0230091/TGHU6423434/TGHU9876007 |  |  | * | * | * | * | Completed- Inovoice not issued
37 | S1798 | J1798 | SANKYU Saudi Arabia | 4500027854 | 2018-04-11 | MSCUJ5582901 | 16 |  | - |  | MSC RAPALLO | 2018-04-13 | 2018-04-13 | 2 | 2018-04-12 | 4139 | 288/3 | 2018-04-16 | 2018-04-16 | 4 | 0 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
38 | S1799 | J1799 | SANKYU Saudi Arabia | 4500027852 | 2018-04-11 | MSCUJ5582927 | 12 |  | - |  | MSC RAPALLO | 2018-04-13 | 2018-04-13 | 2 | 2018-04-12 | 4140 | 288/2 | 2018-04-16 | 2018-04-16 | 4 | 0 | 2018-04-17 | 2018-04-18 | 2018-04-18 | 1 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
39 | S1800 | J1800 | SANKYU Saudi Arabia | 4500027748 | 2018-04-11 | MSCUJ5582893 | 12 |  | - |  | MSC RAPALLO | 2018-04-13 | 2018-04-13 | 2 | 2018-04-12 | 4077 | 290/24 | 2018-04-14 | 2018-04-14 | 2 | 0 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
40 | S1861 | J1861 | SANKYU Saudi Arabia | 4900004753 | 2018-04-12 | MSCUJ5583057 | 7 |  | - |  | MSC FILLIPPA | 2018-04-19 | 2018-04-19 | 7 | 2018-04-16 | 4141 | 297/18 | 2018-04-16 | 2018-04-16 | 0 | 0 | 2018-04-17 | 2018-04-18 | 2018-04-18 | 1 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
41 | S1862 | J1862 | SANKYU Saudi Arabia | 4500027876 | 2018-04-12 | MSCUJ5583024 |  | 4 | - |  | MSC RAPALLO | 2018-04-19 | 2018-04-19 | 7 | 2018-04-16 | 4142 | 295/22 | 2018-04-16 | 2018-04-16 | 0 | 0 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
42 | S1863 | J1863 | SANKYU Saudi Arabia | 4500027785 | 2018-04-12 | MSCUJ5583016 | 9 |  | - |  | MSC RAPALLO | 2018-04-14 | 2018-04-14 | 2 | 2018-04-16 | 4183 | 295/29 | 2018-04-17 | 2018-04-17 | 1 | 0 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
43 | S1864 | J1864 | SANKYU Saudi Arabia | 4500027798 | 2018-04-12 | MSCUJ5583008 |  | 1 | - |  | MSC RAPALLO | 2018-04-14 | 2018-04-14 | 2 | 2018-04-16 | 4184 | 295/30 | 2018-04-17 | 2018-04-17 | 1 | 0 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
44 | S1895 | J1895 | SANKYU Saudi Arabia | 4500027881 | 2018-04-15 | MSCUJ5583891 | 4 |  | - |  | MSC DANIELA | 2018-04-19 | 2018-04-19 | 4 | 2018-04-18 | 4250 | 296/19 | 2018-04-18 | 2018-04-18 | 0 | 0 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
45 | S1896 | J1896 | SANKYU Saudi Arabia | 4500027853 | 2018-04-15 | MSCUJ5583917 | 11 |  | - |  | MSC DANIELA | 2018-04-19 | 2018-04-19 | 4 | 2018-04-18 | 4251 | 296/18 | 2018-04-18 | 2018-04-18 | 0 | 0 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
46 | S1897 | J1897 | SANKYU Saudi Arabia | 4900004752 | 2018-04-15 | MSCUJ5583875 | 3 |  | - |  | MSC FILLIPPA | 2018-04-19 | 2018-04-19 | 4 | 2018-04-18 | 4249 | 297/23 | 2018-04-18 | 2018-04-18 | 0 | 0 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
47 | S1922 | J1922 | SANKYU Saudi Arabia | 4500027884 | 2018-04-16 | MSCUJ5584519 | 4 |  | - |  | MSC RAPALLO | 2018-04-19 | 2018-04-19 | 3 | 2018-04-18 | 4238 | 295/32 | 2018-04-18 | 2018-04-18 | 0 | 0 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
48 | S1956 | J1956 | SANKYU Saudi Arabia | 4500027877 | 2018-04-17 | MSCUJ5584824 |  | 4 | - |  | MSC GAIA | 2018-04-26 | 2018-04-26 | 9 | 2018-04-18 | 4237 | 334/3 | 2018-04-18 | 2018-04-18 | 0 | 0 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
49 | S2015 | J2015 | SANKYU Saudi Arabia | 4500027929 | 2018-04-18 | MSCUJ5585649 |  | 13 | - |  | MSC GAIA | 2018-04-26 | 2018-04-26 | 8 | 2018-04-19 | 4355 | 334/20 | 2018-04-19 | 2018-04-19 | 0 | 0 | 2018-04-20 | [7 empty] | / | / | / | / | Waiting for container to reach at port
50 | S2035 | J2035 | SANKYU Saudi Arabia | 4900004776 | 2018-04-19 | MSCUJ5586043 | 2 |  | - |  | MSC SOLA | 2018-05-04 | 2018-05-04 | 15 | 2018-04-22 | 4418 | 347/1 | 2018-04-22 | 2018-04-22 | 0 | 0 | 2018-04-23 | [7 empty] | / | / | / | / | Waiting for container to reach at port
51 | S2036 | J2036 | SANKYU Saudi Arabia | 4900004755 | 2018-04-19 | MSCUJ5585979 |  | 1 | - |  | MSC FILLIPPA | 2018-04-26 | 2018-04-26 | 7 | 2018-04-22 | 4396 | 297/92 | 2018-04-22 | 2018-04-22 | 0 | 0 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 0 |  |  |  |  | / | / | / | / | Completed- Inovoice not issued
52 | S2095 | J2095 | SANKYU Saudi Arabia | 4900004712 | 2018-04-22 |  |  | 1 | - | [20 empty] | / | / | / | / | Waiting for Manifest
53 | S2126 | J2126 | SANKYU Saudi Arabia | 4500028005 | 2018-04-23 |  |  | 1 | - | [20 empty] | / | / | / | / | Waiting for Manifest